INTERNAL AUDIT PLAN 2026

Kenya Red Cross Society

A risk based plan that drives internal audit activities

Internal audit

11/12/2025

# Table of contents

Contents

Purpose	2

Annual planning	2

1.	Risk assessment	2

2.	Budgetary Allocation	2

3.	Areas of Management Concern	3

4.	Significant Operational Changes	3

5.	Results of Prior Audits:	3

Scope	3

Audit Work plan	4

Budget for Internal audit in 2026	4

Audit Plan for KRCS	5

Human Resources	7

Training Needs	7

Evaluation and metrics	7

COMBINED ASSURANCE MATRIX	8

# Purpose

The purpose of this audit plan is to detail the internal audit activities for the Kenya Red Cross Society for the year 2026. This plan is driven by risk assessment results, area of management concerns, significant operational changes as well as key areas of control weaknesses identified in the year 2025. The goal is to address high risk areas and changes in risk assessments may lead to a change in the plan.

The audit activities will be carried out in accordance to the Global Internal Audit Standards (GIAS) of Internal Auditing and ICPAK guidelines.

# Annual planning

The annual planning process commenced with establishing the audit universe i.e. all auditable area that may include functions, processes, systems and locations.

Risk factor approach and the risk assessment approach were used to establish the areas in the audit universe that are to be audited in the coming financial year.

Under the risk factor approach the following factors (each factor is weighted based on its importance) were considered:

## Risk assessment

Based on the results of the Society’s Risk Assessment process, high-risk areas that need to be audited from the audit universe (all processes or functions that can be audited) were established. This has enabled to focus the audit on high-risk areas instead of all the areas in the audit universe. These risks include:

- Inabilty to achieve our core mandate

- Programming: quality, management, impact

- Financial management and controls

- Governance and leadership, including political interference

- Infrastructure building

- Digital transformation and technology risks

- Staff and volunteer management and engagement

- Health, safety and security of staff, volunteers and beneficiaries (safeguarding, safe programming, PGI, MHPSS)

- Operational: Business Continuity incidents

- Legal, regulatory, compliance, including data protection

- Reputation: political intereference, social media, litigation, compliance

## Budgetary Allocation

The Society’s strategic plan, annual budget, annual work plan, performance contract and other relevant literature were reviewed to establish areas that will be allocated significant funding. These areas include payments to beneficiaries, Human Resources and Procurement.  Such areas are considered to be of higher risk compared to those that receive less funding. The budget for Kenya Red Cross for the year 2026 is Ksh xxxxxxxxxx excluding the Global Fund Program.

## Areas of Management Concern

The Society’s management was engaged to establish areas of concern the Internal Audit needs to focus on in the upcoming year. This includes areas include

- Review of human resources capacity (Skills and numbers) in regions and branches

- Compliance to established SOPs including mileage recharges

- Compliance to statutory payments

- Review of payment processes

- Support finalization of branch profiling

## Significant Operational Changes

The audit clients were engaged to determine significant changes in systems, processes and personnel and the impact they have on the achievement of objectives and management of risks. It was established that

- ERP system has been upgraded from Navision to Dynamics 365 Business Central.

- Organizational restructures and adjustments in processes.

- Automation of key processes such as end to end procurement processes, HR processes, GF SR reporting and warehousing

## Results of Prior Audits:

The outcome of previous internal and external audits was reviewed to identify areas that had significant weak governance, risk management and controls systems and processes and considered them for inclusion in this annual audit plan. Feedback from management on the implementation of audit recommendations and the time lapse since an area was last audited were considered.

| Planning factor | Weight (%) |
| --- | --- |
| Risk assessment | 36% |
| Budgetary allocation | 20% |
| Management concern | 20% |
| Prior audit results | 14% |
| Significant operational changes | 10% |

# Scope

The scope of work in this plan incorporates work covering;

- Kenya Red Cross Society head office, 8 regions and 47 county branches.

- All donor funded programs (except Global Fund)

- Unrestricted income activities by branches and HQ

# Audit Work plan

The audit work plan is indicated below. Being a risk based audit approach, risks and audit processes are indicated. The following assumptions are made in estimating the time taken;

- A full working day is eight (8) hours;

- Frequency denotes number of times an audit activity will be carried out in a year;

- Total hours is derived by multiplying the number of hours spent per audit activity and the frequency;

- Each audit staff will work for 44 weeks in a year taking account of leave days and anticipated public holidays Summary of time spent versus proposed resources (excluding systems audits);

| Entity audited | Man days per plan |
| --- | --- |
| Total man days required | 820 |
| Man days available(3staff X44weeksX5days) | 660 |
| Excess/(Shortfall) Man hours | (160) |

Shortfall will be filled with short-term resources as well as the investigations officer planned to be on boarded next year

# Budget for Internal audit in 2026

Total Budget for internal audit for 2026 in implementation of the audit plan is Ksh.

34,185,308 made up as below;

| Descriptions | Ksh |
| --- | --- |
| Personnel Costs | 20,400,000 |
| Travel | 2,500,000 |
| Governance | 400,000 |
| Communication | 144,000 |
| Professional Fees/Subscriptions | 150,000 |
| Recorder | 50,000 |
| License Costs/ Automation/Servers/Apps | 4,591,308 |
| Training costs | 1,750,000 |
| External Quality Assessment | 3,000,000 |
| Laptops | 1,200,000 |
|  | 34,185,308 |

# Audit Plan for KRCS

The Table below details key risks and processes that have been prioritized for audits. The department proposes to undertake audit assignments as summarized below to address key risk concerns and appropriate coverage of key program areas identified.

|  | Risk category | Engagement | Engagement type | Planning factor | Risk | Risk rating | Frequency | Man days | Time | Resp |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Operational | Review of program management cycle (4 sampled projects) | Assurance | Risk Assessment/ Budgetary Allocations | -Misalignment between project objectives and strategic priorities | High | Semi-annually | 60 | Q2,Q4 | CW |
|  |  |  |  |  | -Cost overruns, budget misuse, or inefficient allocation of funds |  |  |  |  | KM |
|  |  |  |  |  | -Delays that increase costs or reduce benefits. |  |  |  |  |  |
|  |  |  |  |  | -Scope creep |  |  |  |  |  |
|  |  |  |  |  | -Poor quality outputs |  |  |  |  |  |
|  |  |  |  |  | -Ineffective communication |  |  |  |  |  |
|  |  |  |  |  | -Regulatory non-compliance |  |  |  |  |  |
|  |  |  |  |  | -Misaligned objectives |  |  |  |  |  |
|  |  |  |  |  | -Unrealized benefits |  |  |  |  |  |
| 2 | Operational | Human Resources Review (Recruitment and Onboarding) | Assurance | Risk Assessment | -Key personnel may lack the necessary qualifications or certifications for their roles. | High | Annually | 25 | Q3 | A.M.M |
|  |  |  |  |  | -Recruitment Risk |  |  |  |  |  |
|  |  |  |  |  | -Compliance Risk |  |  |  |  |  |
|  |  |  |  |  | -Performance Risk |  |  |  |  |  |
| 3 | Financial | Bank Reconciliations Review | Assurance | Risk Assessment | - Fraud risk | High | Bi Annually | 20 | Q2 &Q4 | CW |
|  |  |  |  |  | - Errors |  |  |  |  | KM |
|  |  |  |  |  | - Incomplete financial records |  |  |  |  |  |
| 4 | Financial | Payments and payables process review | Assurance | Risk Assessment | - Long turnaround time | High | Annually | 25 | Q2 | KM |
|  |  |  |  |  | - Long outstanding payables |  |  |  |  |  |
|  |  |  |  |  | - Inaccurate or Incomplete balances |  |  |  |  |  |
| 5 | Operational | Procurement Review | Assurance | Risk Assessment | Review of controls especially in the system | High | Annually | 25 | Q3 | KM |
| 6 | Operational | CVA review | Assurance | Risk Management | - Adequate design of the project | High | Annually | 25 | Q2 | CW |
|  |  |  |  |  | - Adequate project monitoring (Role of MEAL) -financial and Fraud risks |  |  |  |  |  |
| 7 | Strategic | Risk management review | Assurance | Management request | - Misalignment with organizational goals - Governance and leadership - Mitigation, monitoring and reporting | High | Annually | 20 | Q3 | AM |
| 8 | Operational | 47 Branches audits and 4 regional offices | Assurance | Risk Assessment/ Management Concerns and Budgets / Prior year audit results | - Leadership and Governance, | High | Quarterly | 220 | Q1, | ALL |
|  |  |  |  |  | - Volunteer engagement and Management |  |  |  | Q2, |  |
|  |  |  |  |  | - Control Gaps, |  |  |  | Q3, |  |
|  |  |  |  |  | - Staff Management |  |  |  | Q4 |  |
| 9 | Financial | Review of unrestricted income | Assurance | Risk Management | Expenditure not aligned to mandate | High | Annually | 30 | Q3, | KM |
|  |  |  |  |  | Misuse of funds |  |  |  |  |  |
|  |  |  |  |  | Unbudgeted governance costs |  |  |  |  |  |
|  | Consultancy advisory – PR and communications, Legal, MEAL and Partnerships. |  |  |  |  |  |  | 120 | Q4 | CW |
|  | External Quality Assessment support |  |  |  |  |  |  | 80 |  |  |
|  | Coordination of external audits |  |  |  |  |  |  | 20 |  |  |
|  | Audit & risk committee secretariat |  |  |  |  |  |  | 30 |  |  |
|  | Study leave |  |  |  |  |  |  | 30 |  |  |
|  | Training and Workshops |  |  |  |  |  |  | 25 |  |  |
|  | Adhoc/Investigations |  |  |  |  |  |  | 65 |  |  |
|  | Total man days |  |  |  |  |  |  | 820 |  |  |

# Human Resources

The resources dedicated to Kenya Red Cross will be 3 staff.

The number of staff are adequate to cover the work required to address the risks faced by the Society.

# Training Needs

Due to the ever changing audit and risk trends, it is imperative that the audit team keep abreast of changing requirements. As a result, training is required for the auditors. The following trainings are suggested for the team.

| Training Required | Person to Attend | Justification for Training | Cost of Training (KES) |
| --- | --- | --- | --- |
| Certified Internal Auditor | David Gichuhi | - Address emerging risks - Improved audits | 270,000 |
| Certified Internal Auditor | Amos Muthiani | - Improve quality of audits | 270,000 |
| Certified Internal Auditor | Karani Mwita | - Address emerging risks - Improved audits | 270,000 |

# Evaluation and metrics

Strategy

To ensure an effective audit, proper planning of the audit will be carried out and adequate notice given to the responsible parties before the audit is carried out. Audit issues will be discussed with management and significant issues reported to the audit committee.

Metrics

It is expected that the internal audit activities will result in the following;

- Reliable financial and program information produced;

- Increased level of compliance with policies, procedures and legal regulations;

- Enhanced safeguarding of assets;

- Economic and efficient utilization of resources (reduced wastage).

# COMBINED ASSURANCE MATRIX

The following matrix was developed in order to reduces redundancy, clarifies responsibilities, and provides a comprehensive view of assurance efforts from the top risks identified in 2026

|  | Top risks 2026 | Assurance provider | Engagements |
| --- | --- | --- | --- |
| 1 | Inability to achieve our core mandate | Management, Risk and Compliance | Project risk assessments |
| 2 | Programming: quality, management, impact | Internal audit, Risk & Compliance, | Project Performance audits, Project risk assessments |
| 3 | Financial management and controls | Internal audit, Risk & Compliance & External Auditors | Receivables and payables process review; Cash and Bank Management reviews; Payment process reviews; Continuous business process reviews |
| 4 | Governance and leadership, including political interference | Internal audit, Risk & Compliance | Branch Audits, Continuous monitoring and advisory |
| 5 | Infrastructure building (Opportunities in investing in strategic hubs) | Management, Risk & Compliance | Continuous monitoring and advisory |
| 6 | Digital transformation and technology risks | Systems Audit, Risk & Compliance | IT audits, DT risk assessment and advisory. |
| 7 | Staff and volunteer management and engagement | Internal Audit, Risk & Compliance | HR Audit, Staff and volunteer risk assessment, continuous monitoring and advisory. |
| 8 | Health, safety and security of staff, volunteers and beneficiaries (safeguarding, safe programming, PGI, MHPSS) | Risk & Compliance | Implementation of Safeguarding action plan (guided by safeguarding risk assessment) Staff and volunteer risk assessment, continuous monitoring and advisory. |
| 9 | Operational: Business Continuity incidents | Risk & Compliance | Development and implementation of BCP, including regular testing |
| 10 | Legal, regulatory, compliance, including data protection | Internal Audit; Risk & Compliance | Compliance audit, Continuous compliance monitoring |
| 11 | Reputation: political interference, social media, litigation, compliance | Risk & Compliance | Continuous monitoring and advisory |