## Sheet1
Date | Event | Location/Venue | Detailed activities | Participants | Pre-event planning |  | Budget | Other comments
[5 empty] | Activity | Person responsible
Monday 13 October | Finalization of all plans | Hq, various
Tuesday 14 October | Clean up | South C | Joint clean up of south C with HQ and Nairobi County Staff, South C residents, PNSs | Staff, PNSs, South C MCA, South C residents | Identification of areas to be cleaned
[5 empty] | Communication with area MCA | Elizabeth Osodo
[5 empty] | Staff mobilization (Nairobi County and HQ) | Joram Oranga, Christine Muriuki
[5 empty] | PNS Mobilization | Elizabeth Osodo
[5 empty] | Sourcing of cleaning materials and PPE | Valentine Tindi
Tuesday 14 October | Childrens Home visit | TBC | Visit to a home to interact with the kids and donate food and non-food items | Staff, PNSs | Identification of home | Joram Oranga/Nairobi County |  | To select a home with young children who are available on weekdays ie not in school
[5 empty] | Sourcing for donation items (dry foods, clothes, toys etc) | Cleophas Jpw, Valentine Tindi, Elizabeth, Jamal
[5 empty] | Mobilization of participants | Christine Muriuki, Elizabeth Osodo
[5 empty] | Transportation of items and people | Valentine Tindi
Tuesday 14 October | Hot meals distribution | TBC | Distribution of prepared hot meals to hustlers on the streets of Nairobi (Matatu stage, Jua Kali artisans etc) | Staff, PNSs | Sourcing sponsor for hot meals | Cleophas Jow, Jamal
[5 empty] | Transportation of food | Valentine Tindi
[5 empty] | Mobilization of participants | Christine Muriuki, Elizabeth Osodo
[5 empty] | Transportation of participants | Valentine Tindi
Tuesday 14 October | Tree planting |  | Planting of trees in various locations within Nairobi, especially around the office and South C area (perhaps in schools?) | Staff, PNSs | Sourcing of seedlings | Peter Murgor
[5 empty] | Identification of areas to plant | Peter Murgor
[5 empty] | Mobilization of participants | Christine Muriuki, Elizabeth Osodo
[5 empty] | Transportation of people and seedlings | Valentine Tindi
Wednesday 15 October | Team building |  | Football tournament, Zumba, team building activities, bike races, other matches, children's games from the 80s (kati, blada, bano, shake) | Staff, PNSs, IFRC, ICRC | Identification of venue (Ulinzi/MOW/Nyayo Stadium/Uhuru Gardens) | Mwanakheri, Venant, Brian
[5 empty] | Mobilization of participants | Christine Muriuki, Elizabeth Osodo
[5 empty] | Team building organizer | Christine Muriuki
[5 empty] | Food and refreshments for the day | Christine Muriuki
Thursday 16 October | Emergency Ops Simulation | Embakasi |  |  | Planning and execution of simulation exercise | Anthony Muchiri |  | See separate plan from Anthony
Friday 17 October | Presidential event | State House | See separate program | TBC |  | Monica Orero