## Risk Register Template
KRCS ICT Risk Register
No | OBJECTIVE | RISK CATEGORY | No | RISK(S) | CAUSES | EFFECT | LIKELIHOOD | IMPACT | OVERALL RATING | TREATMENT | Action Points | RISK OWNER | TIMELINE / NEXT REVIEW
|  | LEGAL & REGULATORY | 1 | Compliance risk - protection of personal data and information, which may be required by some of KRCS donors who require GDPR compliance or data protection act of the republic of Kenya | Lack of knowledge on laws Inadequate staff capacity to comply with laws | Fines and penalties Withdrawal of potential donors | 2 | 3 | 6 | Ensure compliance with all laws | Create checklist log for all the required legal requirments Keep checklist log of all requirements including international requirements Carry out regular audits to check for compliance Close audit issues as soon as they arise | Head of IT | 30th Decemeber 2023
|  | HUMAN, SECURITY, HAZARDS | 2 | Occupational Hazard such as backaches and neck pains from long hours at the computer | Automation of business processes | Back pain/ eye trouble Staff unavailable due to increased sick days | 2 | 3 | 6 | Ensure compliance with OSHA act | Dissemination of OSHA act Review physical environment to reduce injuries as per the OSHA act Annual reviews to ensure compliance to the OSHA act | Head of HR
|  |  | 3 | Inadequate staff technical capacity | Rapidly changing technologies / Poor training programme Staff turnover | Recurrence of issues and failure to use best practices or new technology | 2 | 3 | 6 | Create a staff development plan. | Annual review of staffing needs Identification of training needs as part of performance reviews Training plans and budgets taking into consideration the fast changing nature of IT | Head of IT Head of HR | 30th Deember 2023
|  |  | 4 | Inadequate information security | Inadequate infrastructure support such as smoke detectors in server rooms | Loss of critical data in the event of a physical disaster | 2 | 3 | 6 | Adequate data security procedures and policies. | Review and update information security policy Dissemination of the information security policy Training on how to protect information on your devices Ensure adequate physical security for server rooms such as restricted access Regular audit of security vulnerabilities Review adequacy of physical security in server rooms such as smoke detectors Ensure information on PCs are encrypted to ensure data protection | Head of IT Systems Auditor | Quartely Review
|  |  | 5 | Increase in Cyber attack risks | International vulnerability of KRCS ICT infrastructure | Hacking of IT systems | 3 | 3 | 9 | Increased security measures | Review of vulnerability points through penetration tests Implementation of a disaster recovery plan in the event of an attack Training of staff on soft controls to deter attacks from hackers | Head of IT Head of HR | Annual Review
|  |  | 6 | Lack of confidentiality/ privacy risk—the risk that confidential or otherwise sensitive information may be divulged or made available to those without appropriate authority. | Inadequate security measures | Loss of crucial information Fraud due to access to unauthorised information Reputational risk due to leakage of confidential/sensitive information | 2 | 3 | 6 |  | Review of vulnerability points through penetration tests Implementation of a disaster recovery plan in the event of an attack Training of staff on soft controls to deter attacks from hackers Review of access controls to ensure appropriate access. Eg, immediate denial of access to leavers Review system users rights quarterly | Head of IT Head of HR | End year 2023
|  |  | 7 | Fraud through insider attacks/ insider system misuse | Inadequate security measures | Increased loss of funds through fraud | 3 | 3 | 9 |  |  |  | Review Quarterly
|  | SUPERVISORY OPERATIONS | 8 | Integrity risk—the risk that data within information systems cannot be relied on because it is unauthorized, incomplete or inaccurate | Lack of reconciliation procedures to identify incomplete and inaccurate data before it is posted | Incomplete financial reporting | 2 | 3 | 6 | Introduce mechanisms to identify anomalies | End of day/week/month procedures to reconcile information and identify anomalies in good time Address audit issues as soon as they are raised | Head of Departments | Quartely Review
|  |  | 9 | System availability risk/ Lack of system availability | Lack of backup processes Corrupt backup | Loss of service | 1 | 3 | 3 | Disaster Recovery Plans | Document business critical processes Identify recovery point objectives and recovery time objectives Test plans including backups Setup of High Availability (HA) enviroment. | Head of Departments Head of IT | Monthly Review
|  |  | 10 | Infrastructure risk—Risk that KRCS does not have an information technology infrastructure and systems that can effectively support the current and future needs of the organization in an efficient, cost-effective and well-controlled fashion (includes hardware, networks, software, people and processes) | Lack of identification of IT needs at beginning of project Inability to 'forward think' in terms of IT technology | Loss of funds through over investment in IT infrastructure Loss of service Staff reverting to manual way of doing things | 2 | 3 | 6 | Annual planning to include changing IT needs | Identify society needs in advance. Eg, annually Identify IT needs for any new projects or ventures Include IT as a budgetary item in all projects | Head of IT DSG/ Head of Special Programmes | Annual Review
|  |  | 11 | Project risk—the risk of IT projects failing to meet objectives through lack of accountability and commitment | Inability to link IT performance to projects | Inability to meet KRCS objectives | 2 | 3 | 6 | Project planning and funding to be done in advance | Create ICT projects bank account for project impelementation Clear project plan Regular review of project progress |  | Monthly Review